## Slide 1
Trajectory Generation in High Density Environment
Suvo Ganguli
Alberto Speranzon (Presenter)
Apr 9, 2018
Mid-Term Review

## Slide 2: Agenda
Project Overview – 1 min
Summary of Accomplishments – 5 min
Summary of Remaining Work & Challenges – 5 min
PI: GO or NO GO Recommendation – 1 min
Selection Committee Q&A – 3 min
Honeywell Internal

## Slide 3: Project Overview
Deliverables
  Completed
    Development of 2D trajectory generation software
    Tradeoff studies
  Remaining (with proposed change)
    Development of 2D trajectory generation software without using costly / time-consuming global planner, upon encountering pop-up obstacles (a realistic scenario)
    Tradeoff studies
Project Summary
  PI: Suvo Ganguli, Alberto Speranzon
  RTC: CNS
  Project Name: Trajectory Generation in High Density Environment
  Budget: 75K
Problem Statement/Objective:
  Trajectory generation in cluttered environment is a key problem to solve for autonomous operations
  The goal of this project is to understand the tradeoffs between the different parameters used to design trajectory generation in presence of obstacles
Project Status
  YTD Spend: 30K
  Approx % WORK Complete: 50%
  Probability of completion to proposed schedule: 95%
Honeywell Internal

## Slide 4: Summary of Accomplishments
CPU Time (CT) variation with the tradeoff parameters – number of trajectory steps (N), number of obstacles (no), time step (T) and number of states (ns) are as follows:
  CT increases with N as 2N
  CT increases with no as (1- k.e-b.no)
  CT decreased with increase in T (for same horizon length)
  CT decreased from ns = 4 to ns = 6 (due to increase in bandwidth for same weights)
Increase in horizon distance (equivalent to N) leads to:
  Smoother trajectory
  Increase in comfort level
  Decrease in control effort
  This is because with increase in horizon distance, control action can be taken earlier.
  This is at the cost of increase in computation time
Honeywell Internal
Analysis not shown in this slide deck
1 Obstacle
2 Obstacles
Laplacian trajectory – a potential flow based trajectory. Used for global planning. Drawback - does not take into account vehicle dynamics and constraints
MPC trajectory – Model Predictive Control based trajectory. Used for local planning. Benefit - does take into account vehicle dynamics and constraints

## Slide 5: Summary of Tradeoff Charts
Increase in N (equivalent to horizon distance) leads to:
  Smoother trajectory
  Decrease in control effort
  Increase in comfort level
  At the cost of
  Increase in computation time
Computation time
Trajectory Smoothness
Control Effort
(V)
Control Effort
(Chidot)
1
Comfort Level
No. of Time Steps (N)
No. of Time Steps (N)
No. of Time Steps (N)

## Slide 6: Summary of Remaining Work and Challenges
Proposed change
  Development of 2D trajectory generation software without re-computation of initial trajectory using costly / time-consuming global Laplacian planner, upon encountering pop-up obstacles (a realistic scenario)
List of remaining tasks (for proposed change):
  Redefine MPC problem formulation (5K, 3 weeks)
  Update 2D trajectory generation software (20K, 5 weeks)
  Perform tradeoff studies (15K, 3 weeks)
  Create report/slides (5K, 1 week)
Challenges
  Increase in complexity of proposed 2D trajectory generation software
  Increase in effort compared to usage of existing global Laplacian planner
Resources:
  Suvo Ganguli (67%)
  Alberto Speranzon (5%)
Honeywell Internal
Figure shows re-computation of Laplacian Planner trajectory after encountering a pop-up obstacle
Pop-up obstacle
Re-computed Laplacian trajectory
Initial Laplacian trajectory

## Slide 7: PI: GO or NO GO Recommendation
What is the PI’s recommended position on project continuance, based on?
  Recommendation: Continue with the project with the proposed change, which will reduce re-computation time when encountering pop-up obstacles (a realistic scenario)
  Reason: We have met our mid-term goal of
    developing the 2D trajectory software
    performing the tradeoff studies
    in time within budget
  Remaining effort vs time
    2D trajectory generation software development without re-computation of global Laplacian Planner and redo tradeoff studies
    Very likely to complete the project within remaining time (3 months)
  Budget
    Spent 30K out of 35K planned for mid-term review
    45K remaining
  Resource availability
    Suvo – 67% (earlier 50%)
    Alberto – 5%
  Risk
    2D trajectory generation without re-computation of Laplacian Planner likely to take more development time than currently planned for. Trade-off studies may be partially completed.
Honeywell Internal

## Slide 8: Q&A
Honeywell Internal

## Slide 9: Trajectory Variation with No. of Time Steps
With number of states = 4 and number of obstacles = 1, as we increase the number of time steps = 4, 6, 8, we observe that the trajectory gets smoother
  If a “ribbon” being pulled along a circuitous path, the longer the ribbon, the wider the turns.
N = 4
N = 6
N = 8

## Slide 10: CPU Time vs No. of Time Steps (CT vs N)
CPU mean time increases with N as 2N as more computation is required for a larger horizon
N=4
N=6
N=8
N=10

## Slide 11: CPU Time vs No. of Obstacles (CT vs no)
1 Obstacle
2 Obstacles
CPU mean time increases with N as k(1-e-bno) as the number of constraints are active for a longer duration

## Slide 12: Trajectory Generation for Pop-Up Obstacles