## Plan
| Task | Hr B | Hr A | $B | $A |  |  |  | Deliverables (June 30):
[8 empty] | 1 | 2D Design S/W
1 | Problem Setup | 40 | 4 | 5200 | 680 |  |  | 2 | 3D Design S/W
1.1 | Goal | [6 empty] | 3 | PowerPoint Slides
1.2 | Requirements
2 | Design Tools | 400 | 40 | 52000 | 6800 |  |  |  | Mid-term Milestones (Mar 31):
2.1 | 2D Solution | 200 |  |  |  |  | 200 | 1 | Vehicle Model & Occupancy Grid
2.1.1 | Vehicle Model / Occupancy Grid | 16 | [5 empty] | 2 | MPC Problem Setup
2.1.2 | MPC Problem Setup | 16 | [5 empty] | 3 | 2D Design S/W
2.1.3 | MPC S/W & Solution | 120 | [5 empty] | 4 | 2D Tradeoff Graphs
2.1.4 | Tradeoff graphs | 48
2.2 | 3D Solution | 200 | [6 empty] | End-term Milestones (Jun 30):
2.2.1 | Vehicle Model / Occupancy Grid | 16 | [5 empty] | 1 | 3D Design S/W
2.2.2 | MPC Problem Setup | 16 | [5 empty] | 2 | 3D Tradeoff Graphs
2.2.3 | MPC S/W & Solution | 120
2.2.4 | Tradeoff graphs | 48
3 | Report | 72 | 7.2 | 9360 | 1224
3.1 | IP | 16 | 1.6
3.2 | Software | 32 | 3.2
3.3 | Slides | 24 | 2.4
|  |  |  | 66560 | 8704 | 75264
|  | $B/Hr | 130
|  | $A/Hr | 170

## Plan - short
| Task | Hr B | Hr B | $B | $A
1 | Problem Setup | 40 | 4 | 5200 | 680
1.1 | Goal
1.2 | Requirements
2 | Design Tools | 400 | 40 | 52000 | 6800
2.1 | 2D Solution | 200 |  |  |  |  | 200
2.1.1 | Vehicle Model / Occupancy Grid | 16
2.1.2 | MPC Problem Setup | 16
2.1.3 | MPC S/W & Solution | 120
2.1.4 | Tradeoff graphs | 48
2.2 | 3D Solution | 200
2.2.1 | Vehicle Model / Occupancy Grid | 16
2.2.2 | MPC Problem Setup | 16
2.2.3 | MPC S/W & Solution | 120
2.2.4 | Tradeoff graphs | 48
3 | Report | 72 | 7.2 | 9360 | 1224
3.1 | IP | 16 | 1.6
3.2 | Software | 32 | 3.2
3.3 | Slides | 24 | 2.4
|  |  |  | 66560 | 8704 | 75264
|  | $B/Hr | 130
|  | $A/Hr | 170
trest

## Actuals
To be updated
| Task | Hr B | Actual | Hr A | Actual |  |  |  | Suvo | Others | PPC | Cost (K)
[7 empty] | Jan | 7 | 10 |  |  | 1.3
1 | Problem Setup | 40 | 40 | 4 | 1 |  |  | 14 | 19 |  |  | 2.47
1.1 | Goal |  | 16 |  | 1 |  |  | 21 | 22 |  |  | 2.86
1.2 | Requirements |  | 24 |  |  |  |  | 28 | 40 |  |  | 5.2
[7 empty] | Feb | 4 | 11 |  |  | 1.43
2 | Design Tools | 400 | 157 | 40 | 5 |  |  | 11 | 11 |  |  | 1.43
2.1 | 2D Solution | 200 | 157 |  | 5 |  |  | 18 | 21 |  |  | 2.73
2.1.1 | Vehicle Model / Occupancy Grid | 16 | 16 |  |  |  |  | 25 | 18 |  |  | 2.34
2.1.2 | MPC Problem Setup | 16 | 18 |  | 5 |  | Mar | 4 | 17 | 10 |  | 3.91
2.1.3 | MPC S/W & Solution | 120 | 120 |  |  |  |  | 11 | 28 |  |  | 3.64
2.1.4 | Tradeoff graphs | 48 | 3 |  |  |  |  | 18 | 39 |  |  | 5.07
[8 empty] | 25 | 12.5 |  |  | 1.625
2.2 | 3D Solution | 200 | 0 |  | 0 |  | Apr | 1 |  |  |  | 0
2.2.1 | Vehicle Model / Occupancy Grid | 16 | [5 empty] | 8 |  |  |  | 0
2.2.2 | MPC Problem Setup | 16 | [5 empty] | 15 |  |  |  | 0
2.2.3 | MPC S/W & Solution | 120 | [5 empty] | 22 |  |  |  | 0
2.2.4 | Tradeoff graphs | 48 | [5 empty] | 29 |  |  |  | 0
[7 empty] | May | 6 |  |  |  | 0
3 | Report | 72 | 0 | 7.2 | 0 |  |  | 13 |  |  |  | 0
3.1 | IP | 16 |  | 1.6 | 0 |  |  | 20 |  |  |  | 0
3.2 | Software | 32 |  | 3.2 | 0 |  |  | 27 |  |  |  | 0
3.3 | Slides | 24 |  | 2.4 | 0 |  | Jun | 3 |  |  |  | 0
[8 empty] | 10 |  |  |  | 0
|  |  | 197 |  | 6 | 203 |  | 17 |  |  |  | 0
[5 empty] | 1.02 |  |  | 24 |  |  |  | 0
|  | $EngA | 170 | [5 empty] | 248.5 | 10 |  | 34.005
|  | $EngB | 130
[7 empty] | Remaining |  |  |  |  | 40.995
|  | Cost (A/B) | 25.61
|  | Total | 26.63